## Summary
Project Name | : | Green University of Bangladesh
Project Manager | : | Tarqul Alam O-pi
Project ID | :
Test types | : | usability &integrity testing
Test Case Preparation Date | :
Version | : | 1
Total scenarios | : | 5
Total Test case | : | 5
Test case with steps | :
Total Passed test case | : | 0
Total Failed test case | : | 0
Total blocked test case | : | 0
Total untested | : | 0
Total | : | 0

## Test_Scenarios
Test Scenario No. | User Type | Module | SubModule | Sub-Submodule | Test Scenario | TC | POC | Priority | Planned Execution Date | Actual Execution Date
TS001 | All User | Login & Logout | Enter |  | Verify UI and Functionality of this module
TS002 |  | Home | View |  | Verify UI and Functionality of this module
TS003 |  | Result | View |  | Verify UI and Functionality of this module
TS004 |  | Course Evaluation | Edit |  | Verify UI and Functionality of this module
TS005 |  | Pre-Registration | Edit |  | Verify UI and Functionality of this module

## Test_cases
Test Case Number | Test Case Name/Title | Description | Expected Result | Actual Result | Category | Test results | Defect ID | Defect Severity | Comments | Test Data | Planned Execution Date | Actual Execution Date | Firefox | Chrome | IE | Edge | Executed By | Browser Execution By
TS001_TC001 | Enter>UI and usability and integrity View | Verify if Enter>UI and usability and integrityView is working or not | It should work | It worked | Functional | Pass
TS002_TC001 | Home> View | Verify if Enter>UI Login & Logout Std id and pass and usability and integrityView is working or not | It should work | It worked | Functional | Pass
TS003_TC002 | Result > View | Verify if Enter> student information usability and integrityView is working or not | It should work | It worked | Functional | Pass
TS004_TC001 | Course Evaluation > Edit | Verify if Enter>Indivisul faculty marking and usability and integrityView is working or not | It should work | It worked | Functional | Pass
TS005_TC001 | Pre-Registration > Edit | Verify if Enter>Indivisul Pre-Registration course add marking and usability and integrityView is working or not | It should work | It worked | Functional | Pass

## Sheet1
3332 | DRM | Trivial | CONFIRMED | --- | Admin login ¦¦Management ¦¦User Management ¦¦+New User ¦¦It is not specified which fields are mandatory and which fields are not
3333 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Management ¦¦User Management ¦¦+New User ¦¦Blank spaces at 'Name' and 'User Name' field get accepted by the system
3334 | DRM | Major | CONFIRMED | --- | Admin ¦¦Management ¦¦User management ¦¦user edit ¦¦Duplicate user name can be set
3335 | DRM | Enhancement | CONFIRMED | --- | Admin ¦¦Management ¦¦User management ¦¦user edit ¦¦Deactivating and re-activating a user' feature is not available
3336 | DRM | Trivial | CONFIRMED | --- | Admin login ¦¦Management ¦¦Parliament member ¦¦+New User ¦¦It is not specified which fields are mandatory and which fields are not
3337 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Management ¦¦Parliament member ¦¦+New User ¦¦Blank spaces at 'Name' and 'Constituency' and 'Party' field get accepted by the system
3338 | DRM | Enhancement | CONFIRMED | --- | Admin login ¦¦Management ¦¦Parliament member ¦¦There should be Delete parliament member options available
3339 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Management ¦¦Room ¦¦+Add new room ¦¦Blank spaces at 'Name' get accepted by the system
3340 | DRM | Minor | CONFIRMED | --- | Admin login ¦¦Management ¦¦Committees ¦¦+Add new Committees ¦¦Clciking Submit buttpn without selecting any term get accepted and shows term as "0nth".
3341 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Management ¦¦Committees ¦¦+Add new Committees ¦¦Blank spaces at 'Name' get accepted by the system
3342 | DRM | Enhancement | CONFIRMED | --- | Admin login ¦¦Management ¦¦Committees ¦¦Spelling mistake-Term should be set as "12th' not as '12nth'
3343 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Proceedings ¦¦Committees ¦¦+Add new Proceedings ¦¦Blank spaces at 'Meeting name' get accepted by the system
3344 | DRM | Enhancement | CONFIRMED | --- | Admin ¦¦Proceeding ¦¦Add new proceeding ¦¦System should give warning message when duplicate data is being entered to prevent duplicate proceeding entry
3345 | DRM | Enhancement | CONFIRMED | --- | Admin ¦¦Proceeding/Recording ¦¦There should be searching and Filtering features of proceeding and recording
3346 | DRM | Enhancement | CONFIRMED | --- | Admin ¦¦Proceeding/Recording ¦¦There should be Delete proceeding and recording functionality
3347 | DRM | Major | CONFIRMED | --- | Admin/All user ¦¦Home ¦¦Scorilling doesnt work
3348 | DRM | Enhancement | CONFIRMED | --- | Admin/Director recording ¦¦Record ¦¦Clicking on Record Stop button should give confirmation message as once clicked record stop button by mistake Recording director can't resume the recording process
3349 | DRM | Major | CONFIRMED | --- | Admin ¦¦task management ¦¦If a Recording time is less than split time , that split of recording is not shown in task management audio split
3350 | DRM | Major | CONFIRMED | --- | Admin/Reporting officer ¦¦Transcription ¦¦Marking that has been done in recording module should be visible in transcription module while transcribing
3351 | DRM | Normal | CONFIRMED | --- | Reproting officer ¦¦ Transcribe ¦¦ Unicode and ANSI radio button is shown only in Admin UI not in Transcriber UI
3352 | DRM | Minor | CONFIRMED | --- | Reporitng officer ¦¦ Transcribe ¦¦ Shortcut key does not work for Reporting officer but for admin only
3353 | DRM | Normal | CONFIRMED | --- | Admin ¦¦Transcription ¦¦Compile report ¦¦Drafted portion should not be visible in admin panel to compile report or drafted portion should not be added in final report
3354 | DRM | Normal | CONFIRMED | --- | Director Reporting/Recording Supervisor ¦¦ Home ¦¦ "task Management" list is not visible in Home UI but visible in "Task Management UI" for Director Reporting
3355 | DRM | Enhancement | CONFIRMED | --- | All User ¦¦ Home ¦¦ user profile detail (name and role) should be visible at navbar when logged in

## Test steps
Test Case Number | Test Step ID | Test Steps | Expected Result | Test Results | Test Data

## Tracability Matrix
SNO | Requirement ID | Test Scenario | TestCase | Count

## Review Comment
SL No | Document name | Section name | Review Comment | Author name | Solution | Review Comment | Reviewed By | Reviewed Date | Status